## Slide 1: Tax Billing Annual Billing Process/Vision Interface
Jarona Twine & Tom Keefe
NASU 2025 Wednesday, October 1st – Friday, October 3rd
Nashville, TN

## Slide 2: Yearly – CoR
Personal Property
Maintain master files for:
  Business Personal Property
  Mobile Homes
  Watercraft
  Other applicable property types
Real Estate
Maintain and transfer ownership throughout the year in the appraisal system
  Use Parcel Maintenance (LR0058) for additional changes
Maintain Deferments

## Slide 3: January – CoR & KIS
Personal Property and Real Estate
Establish a cut-off date for the last day to update and enter data into the system
Keystone Only:
  Run Bad Parcel ID Report (PT0106)
  Perform Delete Bad Parcel Process (PT0107)

## Slide 4: February 1st Week - CoR
Personal Property and Real Estate
Run the appraisal interface to update real estate values for land and improvements
Note:
  This process can be run as often as needed.
  This does not update the land or building information (e.g., TALAND).

## Slide 5: February 2nd Week - CoR
Personal Property & Real Estate
Verify and run matching process for master records.
Confirm each record contains:
  Account Number
  District Code
  Tax Code
  Status
Real Estate
Run Parcel Audit Reports (PT0546)
Run Meta Queries

## Slide 6: February 3rd / 4th Week – CoR & KIS
Personal Property
  Run Parcel Audit Reports (PT0546)
  Run Meta Queries
Real Estate
  Archive Abstracts Prior to Year End

## Slide 7: March 1st Week – CoR & KIS
Personal Property
Run meta queries for all permanent files that are in a L, LL or U status.
Personal Property and Real Estate
Keystone Only:
  Backup of Abstract, Absprop, Personal, Account, Real, etc.

## Slide 8: March 2nd Week – CoR
Personal Property & Real Estate
Create Tax Codes (PT0139) for the next billing year and set up rates (one-time task)
Run Meta Queries (township, ownership, value tax codes, etc.)
Real Estate
  Set up Interest and Penalty

## Slide 9: March 3rd Week – CoR
Real Estate
  Run the final interface update
  Run Annual Year End (PT0108) and create Abstracts - Billing Records for Personal and Real Estate
Personal Property
  Run Annual Year End (PT0108) and create Abstracts - Billing Records for Business Personal Property and Watercraft

## Slide 10: March 4th Week – CoR
Personal Property
Run Motor Vehicle Year End
Generate Book Values for Personal Property and review
Print Personal Property Book
Calculate Levy after the Personal Property Book has been printed
Notify the Treasurer the Personal Property Book is completed and deliver by April 1st
Real Estate
Print Land Book and review
Make corrections at the Parcel, Land, or Building levels if needed
If there are errors or discrepancies, run the Levy Correction to make changes and recalculate as needed to achieve a final Land Book report (convert to PDF to preview)
Perform Value Adjustment Calculation
Add Exemptions – Data entry in Annual Valuation Maintenance (PT0165) → Exemptions button (PT0173)
Calculate Final Assessment with Exemptions (Elderly, Veterans, etc.)
Notify the Treasurer the Land Book is completed
Set up Parameters – Change Year (one-time task)

## Slide 11: April 1st Week – Treasurer
Personal Property
Set up Interest and Penalty Parameters for next billing years (e.g., 24A, 24V, 25V)
Run Prepay Audit Report for Personal Property payments
Apply Personal Property Prepayments
Real Estate
Set up Interest and Penalty Parameters for Real Estate bills (e.g., 24A – Due 1, 24B – Due 2, 24U – Utilities)
Run Annual Year End
Run Prepayment Audit Report for Real Estate payments and print separately from Personal Property to compare with bills that do not yet exist to ensure accuracy
Make any necessary adjustments in the Prepayment Entry screen

## Slide 12: April 2nd Week – Treasurer
Personal Property
Print the Tax Bills
Real Estate
Split Tax Bills into two halves
Apply Real Estate Payments
Review to ensure there are no errors

## Slide 13: April 3rd Week – Treasurer
Personal Property and Real Estate
Receive proofs back from BMS
Merge Tax Bills to Collections by merging Due 1 and Due 2 bills at the same time to make them collectible
  Note: This process can take a little while to fully run

## Slide 14: April 19th – Treasurer
Personal Property and Real Estate
Verify Interest and Penalty parameters
Third party vendor will mail out tax bills

## Slide 15: NASU 2025 Session Surveys – we want your feedback!
All responses will be entered into a drawing for a $50 Amazon Gift Card.
Drawing to take place Friday at lunch. There will be multiple winners!
Link to session survey or scan this QR code (also on the agenda)